CFM AND CTE: PROJECT MANAGEMENT AND CLIENT READINESS

# Managing Team Responsibilities, Quality, and Project Changes

Detailed practice, calculation, decision-making, and assessment

| GRADES 9-12 | TIME 2 x 42 min | GROUPING I / pairs / whole | PRODUCT Recover |
| --- | --- | --- | --- |

YOUR CHALLENGE Assign responsibilities, monitor progress, resolve a missed deadline, document quality, and control changes to a shared project.

# New York CFM Connections: Planning, Team Accountability, Quality, and Professional Communication

Teamwork is not simply dividing a project into equal pieces. Effective teams match tasks to skills, clarify ownership, share progress early, use consistent quality checks, and document changes. Problems should be addressed through evidence and respectful communication rather than blame.

| Term | Student-friendly meaning |
| --- | --- |
| Owner | The person accountable for completing or coordinating a task. |
| Quality criterion | A specific requirement used to judge work. |
| Status update | A brief report of progress, risks, and next actions. |
| Version control | A system for identifying and protecting the correct file or revision. |
| Scope change | A requested adjustment to agreed work. |
| Escalation | Seeking help from the appropriate person when a problem cannot be resolved at the current level. |

CLASSROOM USE All people, employers, figures, brackets, and documents in this packet are fictional. Never place a real Social Security number, employer ID, bank number, or tax document in classroom work.

# Part 1 - Build a Responsibility Map

Four-person team must research, write, design, check accessibility, manage files, and present.

| Task | Primary owner | Reviewer/backup | Due date | Evidence |
| --- | --- | --- | --- | --- |
| Research |  |  |  |  |
| Writing |  |  |  |  |
| Design |  |  |  |  |
| Accessibility |  |  |  |  |
| File control |  |  |  |  |
| Presentation |  |  |  |  |

Every task needs one accountable primary owner even when several people help.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# Part 2 - Interpret a Midproject Status Report

Research complete; writing 80%; design blocked by missing final text; accessibility not started; presentation outline complete; two weeks remain.

| Workstream | Status | Dependency/risk | Next action | Owner/deadline |
| --- | --- | --- | --- | --- |
| Research |  |  |  |  |
| Writing |  |  |  |  |
| Design |  |  |  |  |
| Accessibility |  |  |  |  |
| Presentation |  |  |  |  |
| Overall |  |  |  |  |

Use facts from the report rather than blaming a teammate.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# Part 3 - Create a Quality-Control Checklist

Check accuracy, completeness, readability, accessibility, file naming, links, source use, and approval.

| Criterion | Check method | Pass evidence | Owner |
| --- | --- | --- | --- |
| Accuracy |  |  |  |
| Completeness |  |  |  |
| Readability |  |  |  |
| Accessibility |  |  |  |
| Files |  |  |  |
| Links |  |  |  |
| Sources |  |  |  |
| Approval |  |  |  |

“Looks good” is not a measurable check.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# Part 4 - Evaluate a Client Change Request

Client requests a second flyer, translated version, and new video with ten days remaining; original budget and deadline are unchanged.

| Requested change | Impact | Question | Recommendation |
| --- | --- | --- | --- |
| Second flyer |  |  |  |
| Translation |  |  |  |
| Video |  |  |  |
| Budget |  |  |  |
| Deadline |  |  |  |
| Quality |  |  |  |

Do not promise unapproved work.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# Part 5 - Write a Team Recovery Plan

Create a 175-225 word response to the blocked design and change request.

| Plan element | Action/evidence |
| --- | --- |
| Immediate action |  |
| Responsibility |  |
| Revised sequence |  |
| Quality protection |  |
| Client response |  |
| Escalation |  |
| Review |  |

Include a respectful status message and decision deadline.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________